## Project Plan
DCJS Financial and Grant Management Assessment
Deloitte
Workstream |  | Owner | Start Date | Finish Date | Onsite / Remote | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27 | 2019-06-03 | 2019-06-10
Index | Phase 1 - Current state assessment across key financial management areas |  | 2019-03-11 | 2019-06-07
1 | Planning |  | 2019-03-11 | 2019-03-26
1.1 | Onboard Core Deloitte Team | Deloitte | 2019-03-11 | 2019-03-25 | Remote
1.2 | Build project plan | Deloitte | 2019-03-11 | 2019-03-25 | Remote
1.3 | Establish Status Reporting Cadence & Structure | Deloitte, DCJS | 2019-03-15 | 2019-03-26 | Remote
1.4 | Identify Key Stakeholders and schedule project kick-off meeting(s) | Deloitte | 2019-03-15 | 2019-03-25 | Remote
1.5 | Setup Engagement Collaboration Site (SharePoint/ShareFile) and grant access to team members | Deloitte | 2019-03-13 | 2019-03-25 | Remote
2 | Kick-Off Meeting |  | 2019-03-13 | 2019-04-04
2.1 | Build draft kick-off deck | Deloitte | 2019-03-13 | 2019-03-22 | Remote
2.2 | Finalize materials for kickoff meeting | Deloitte | 2019-03-25 | 2019-03-26 | Both
2.3 | Build template for status report and socialize deck | Deloitte | 2019-03-20 | 2019-03-26 | Remote
2.4 | Data Requests and Templates | Deloitte, DCJS | 2019-03-13 | 2019-04-04
2.4.1 | Build data requests list and share with client | Deloitte | 2019-03-13 | 2019-03-20 | Remote
2.4.2 | Organize data received | Deloitte, DCJS | 2019-03-15 | 2019-04-01 | Remote
2.4.3 | Review data received and develop baseline understanding of in-scope processes | Deloitte | 2019-03-15 | 2019-04-04 | Remote
3 | Assess Current State |  | 2019-03-15 | 2019-05-10
3.1 | Document Current State Assessment | Deloitte | 2019-03-15 | 2019-05-10 | Both
3.1.1 | Review existing policies and procedures | Deloitte | 2019-03-26 | 2019-04-25 | Both
3.1.2 | Schedule workshops and interviews | Deloitte, DCJS | 2019-03-15 | 2019-03-26 | Remote
3.1.3 | Conduct interviews/walkthroughs with process owners on current state processes and desired future state (Includes process, control and system walkthrough for each process area): | Deloitte, DCJS | 2019-03-27 | 2019-05-07 | Onsite
3.1.3.1 | Budgeting and Planning | Deloitte, DCJS | 2019-03-27 | 2019-04-03 | Onsite
3.1.3.2 | Budget to Actuals | Deloitte, DCJS | 2019-03-27 | 2019-04-03 | Onsite
3.1.3.3 | Controllership Functions: | Deloitte, DCJS | 2019-04-03 | 2019-04-24 | Onsite
3.1.3.3.1 | Procure to Pay including payments and expenses | Deloitte, DCJS | 2019-04-03 | 2019-04-10 | Onsite
3.1.3.3.2 | Accounts Receivable | Deloitte, DCJS | 2019-04-10 | 2019-04-17 | Onsite
3.1.3.3.3 | Cash Management | Deloitte, DCJS | 2019-04-10 | 2019-04-17 | Onsite
3.1.3.3.4 | Close and Consolidation | Deloitte, DCJS | 2019-04-17 | 2019-04-24 | Onsite
3.1.3.4 | Financial and Management Reporting | Deloitte, DCJS | 2019-04-17 | 2019-04-24 | Onsite
3.1.3.5 | Cost Accounting and Allocations | Deloitte, DCJS | 2019-04-24 | 2019-05-01 | Onsite
3.1.3.6 | Grants Management (Includes: grants administration process to include financial reporting, grants oversight, cost allocation, award budgets, and collection of match) | Deloitte, DCJS | 2019-04-24 | 2019-05-07 | Onsite
3.1.4 | Document notes | Deloitte, DCJS | 2019-03-27 | 2019-05-08 | Remote
3.1.5 | Perform follow-up from interviews via focus groups, in-person, phone interviews, and surveys as required | Deloitte, DCJS | 2019-03-27 | 2019-05-10 | Both
3.1.6 | Distribute meeting minutes to interview participants for validation | Deloitte, DCJS | 2019-03-28 | 2019-05-10 | Remote
3.1.7 | Use meeting minutes in conjunction with available documentation to document current state | Deloitte | 2019-03-28 | 2019-05-10 | Both
3.2 | IT / Technology Structure | Deloitte, DCJS | 2019-03-26 | 2019-05-01 | Onsite
3.2.1 | Interview client to understand current technologies in place intra and inter-department to facilitate financial transactions, controls, reconciliations and reporting | Deloitte, DCJS | 2019-03-26 | 2019-04-24 | Onsite
3.2.2 | Interview client to understand systems used to oversee and administer the programs such as Grants Management Online Information System (GMIS Online) and Cardinal | Deloitte, DCJS | 2019-03-26 | 2019-05-01 | Onsite
3.3 | Assess overall risks and controls and Risk of Material Misstatements or errors | Deloitte | 2019-04-01 | 2019-05-10 | Both
3.4 | Identify current controls and monitoring procedures in use (if any) based on federal grant requirements, DJCS policies and ARMICS | Deloitte, DCJS | 2019-03-28 | 2019-04-26 | Both
3.5 | Identify relevant regulatory framework components | Deloitte, DCJS | 2019-03-26 | 2019-04-04 | Both
4 | Assess current controls and monitoring procedures in use based on federal grant requirements, DJCS policies and ARMICS |  | 2019-04-04 | 2019-05-15
4.1 | Design controls testing strategy i.e. testing to assess design effectiveness and operating effectiveness of the controls for federal grants | Deloitte | 2019-04-04 | 2019-04-23 | Remote
4.2 | Select sample population | Deloitte, DCJS | 2019-04-24 | 2019-04-30 | Both
4.3 | Perform Testing on Controls and available documentation | Deloitte | 2019-05-01 | 2019-05-15 | Onsite
5 | Compliance Analysis |  | 2019-03-28 | 2019-05-15
5.1 | Inventory policies and procedures specific to the Commonwealth of Virginia and applicable federal financial and grants management regulations | Deloitte | 2019-03-28 | 2019-04-17 | Remote
5.2 | Document compliance requirements based on leading practices | Deloitte | 2019-04-10 | 2019-04-30 | Remote
5.3 | Perform comparison | Deloitte | 2019-05-01 | 2019-05-15 | Both
6 | Maturity Survey |  | 2019-03-25 | 2019-05-03
6.1 | Finalize Capability Maturity Model tool / survey | Deloitte | 2019-03-25 | 2019-04-01 | Remote
6.2 | Launch maturity survey | Deloitte, DCJS | 2019-04-03 | 2019-04-12 | Both
6.3 | Collate/analyze results of maturity survey to arrive at desired 'To-Be' state | Deloitte | 2019-04-15 | 2019-04-26 | Remote
6.4 | Review results of maturity survey | Deloitte | 2019-04-29 | 2019-05-03 | Onsite
7 | Benchmarking & Leading Practice Evaluation |  | 2019-04-29 | 2019-05-22
7.1 | Perform benchmarking against leading practices for findings from - current state assessment, IT/Technology assessment, controls testing and Compliance analyses | Deloitte | 2019-04-29 | 2019-05-10 | Remote
7.2 | Identify gap / perform gap analysis | Deloitte | 2019-05-06 | 2019-05-15 | Both
7.3 | Draft recommendations based on gap analysis (i.e. recommendations for Quick Wins and Long Term gains) | Deloitte | 2019-05-15 | 2019-05-22 | Both
8 | Develop Recommendations |  | 2019-03-26 | 2019-06-07
8.1 | Develop prioritization criteria for improvement opportunities | Deloitte, DCJS | 2019-03-26 | 2019-04-04 | Onsite
8.2 | Identify initiatives based on identified opportunities for improvement including future state operating model | Deloitte | 2019-05-15 | 2019-05-22 | Both
8.3 | Identify technology related initiatives based on identified opportunities for improvement | Deloitte | 2019-05-15 | 2019-05-22 | Both
8.4 | Finalize the various opportunities and delineate into discrete initiatives | Deloitte | 2019-05-15 | 2019-05-22 | Both
8.5 | Prioritize initiatives and develop implementation roadmap | Deloitte, DCJS | 2019-05-22 | 2019-05-29 | Both
8.6 | Review and finalize recommendations, roadmap, and/or automation requirements and review with Executive Sponsor and Program Leadership | Deloitte, DCJS | 2019-05-28 | 2019-05-31 | Both
8.7 | Refine as necessary based on feedback | Deloitte | 2019-06-03 | 2019-06-07 | Both
9 | Final Deliverable |  | 2019-05-22 | 2019-06-07
9.1 | Consolidate approach, findings and recommendations from the current state assessment, document review and compliance analysis in final report / package | Deloitte | 2019-05-22 | 2019-05-31 | Both
9.2 | Conduct reviews of final deliverable | Deloitte | 2019-05-28 | 2019-05-31 | Both
9.3 | Submit final report post final report-out meeting | Deloitte | 2019-06-03 | 2019-06-07 | Both

## Preliminary Request
No | Initial information request list | Key contact | Comments | Due date | Status
1 | Organization Chart and Department Overview
1.1 | Organization Chart and Stakeholder View for in-scope processes: -Budgeting & planning, budget to actuals, grants management and oversight, payables and expense management, financial and management reporting, controllership, cost accounting and allocations
1.2 | Roles and Responsibilities including contact information for process leads
1.3 | Current Chart of Accounts
2 | Relevant Policies and Procedures
2.1 | General Accounting Policies (if any)
2.2 | Process Specific Policies, Standard Operating Procedures, Job Aids, End User Training Documents, Process Flows for the following process areas (if any):
2.2.1 | Budgeting and Planning
2.2.2 | Budget to Actuals
2.2.3 | Controllership Functions:
2.2.3.1 | Procure to Pay including payments and expenses
2.2.3.2 | Accounts Receivable
2.2.3.3 | Cash Management
2.2.3.4 | Close and Consolidation
2.2.4 | Financial and Management Reporting
2.2.5 | Cost Accounting and Allocations
2.2.6 | Grants Management (Includes: grants administration process to include financial reporting, grants oversight, cost allocation, award budgets, and collection of match)
2.3 | Current internal control documentation (if any)
3 | Grants
3.1 | Current Inventory of Sub-Awards
3.2 | Sub-Award Agreements
3.3 | Current Internal Controls Listing or Matrix
3.4 | Federal Financial Report (FFR) or SF-425 for the current year and 2 prior years
3.5 | Current Inventory of Active and Inactive projects
4 | Reporting
4.1 | Current Reporting Checklists or Templates
4.2 | Sample Final Progress Reports
4.3 | Sample Annual Performance Reports
4.4 | Inventory and samples of the financial management and grants management reporting currently being administered by DCJS
5 | Accounting
5.1 | Budget reports for Commonwealth of Virginia for the current year and 2 prior years
5.2 | Transaction Reports for Revenues / Drawdowns
5.3 | Budget to Expenditure Reconciliation Reports
5.4 | Revenue to Expenditure Reconciliation Reports
5.5 | Cash / Bank Reconciliation Reports
6 | State Auditor/Internal Audit/Assessment Reports
6.1 | Internal Audit/Assessment Reports (if any)
6.2 | Process Specific KPIs/KRIs list
6.3 | Risk and Controls Documentations (RCMs etc.)
6.4 | Risk Assessment Results (if any)
6.5 | List of applicable federal financial and grants management regulations for in-scope processes
7 | Regulatory Guidance
7.1 | Inventory of the current regulatory guidance (Federal, State of Virginia, etc.) currently being referenced by DCJS over financial management and grants administration
8 | Technology Review
8.1 | Inventory of financial systems currently being used (e.g., Grants Management Online Information System (GMIS Online), Cardinal, general ledgers system, sub ledger system, external data sources/third party applications etc.)
8.2 | SoD/Division of roles and responsibilities operating each of the aforementioned systems
8.3 | System-mapping key internal relationships / Cross functional process maps (budgeting & planning versus payables and expense management, grants versus allocations, reconciliations versus reporting, etc.)
9 | Others
9.1 | Which business units are expected to be included for this assessment?
9.2 | Are there other on-going initiatives that could impact the project deployment?

## Stakeholders
Please provide the list of stakeholders / process owners who will need be a part of the current state assessment
Name | E-mail address | Role | Job Title | Desired Level of Involvement
Megan Peterson | megan.peterson@dcjs.virginia.gov | Project Manager | Chief Deputy Director
Albert Stokes | albert.stokes@dcjs.virginia.gov | Business Owner - Grants | Grants Manager
Bill Dodd | bill.dodd@dcjs.virginia.gov |  | Grants Administration Supervisor
Deandrea Williams | deandrea.williams@dcjs.virginia.gov |  | Grant Support Liaison
Mark Fero | mark.fero@dcjs.virginia.gov |  | Grants Compliance Supervisor
Beverly Johnson | beverly.johnson@dcjs.virginia.gov |  | Grant Support Specialist
Virginia Sneed | virginia.sneed@dcjs.virginia.gov |  | Grant Support Specialist
Andy Woolridge | andy.woolridge@dcjs.virginia.gov |  | Grant Fiscal Monitor
Monica Darden | monica.darden@dcjs.virginia.gov | Business Owner - Finance | Chief Financial Officer
Connie Fisher | connie.fisher@dcjs.virginia.gov |  | Financial Analyst
Linda Jafari | linda.jafari@dcjs.virginia.gov |  | Budget Analyst
Karen Roth | karen.roth@dcjs.virginia.gov |  | Sr. Accountant
Nichole Krol | nichole.krol@dcjs.virginia.gov |  | Sr. Accountant
Tom Fitzpatrick | thomas.fitzpatrick@dcjs.virginia.gov | Business Owner - Programs | Director of the Division of Programs and Services

## Meeting Requests-Schedule
Below is the list of requested meetings and the times / days that are targeted
Meeting Subject | Meeting Purpose | Suggested Attendees | Targeted Days/Times | Scheduled? | Remote or In-Person Required?
Project Kick-off | Set the common understanding of the purpose of the project, scope, timeline, team and stakeholders | Deloitte, DCJS TBD | 2019-03-26 |  | In-Person

## Question List
Below is the list of open questions being tracked by the Deloitte team
Question | Owner | Response | Targeted Close Date | Follow-up Required?